## Overview
Category | Item | Value | Notes
Project | Jira Project Key | TOS | Use one company-managed software project for TreasuryOS.
Project | Recommended Board | TreasuryOS Product Ops | Use one main Kanban board first; split later only if scale demands it.
Board | Board Type | Kanban | Best default for mixed feature, bug, ops, and release work.
Board | Columns | Backlog ¦ Ready ¦ In Progress ¦ In Review ¦ Ready for Release ¦ Released ¦ Blocked | Keep the workflow visible and simple.
Hierarchy | Premium Jira | Initiative -> Epic -> Story/Task/Bug/Incident/Change/Release | Use Advanced Roadmaps if available.
Hierarchy | Standard Jira | Epic -> Story/Task/Bug/Incident/Change/Release | Use labels like initiative:solana-testnet if Initiatives are unavailable.
Issue Type | Epic | Major product area or delivery stream | Examples: Solana Testnet Enablement, AI Advisory Layer.
Issue Type | Story | User-facing or business-facing value | Use when the customer or operator experiences the outcome directly.
Issue Type | Task | Engineering or ops work | Use for implementation, infra, docs, and operations.
Issue Type | Spike | Research or investigation | Use when the answer is not known yet.
Issue Type | Bug | Broken behavior or regression | Always assign severity and environment.
Issue Type | Incident | Production degradation or outage | Always link a postmortem before closure.
Issue Type | Change | Controlled config/runtime/deployment change | Use for Railway, Vercel, Cloudflare, or secrets changes.
Issue Type | Release | Deployment bundle or milestone shipment | Every meaningful rollout should have one.
Component | Core Components | dashboard, landing-page, api-gateway, solana, ai, entities, wallets, transaction-cases, reports, audit, kyc, security, infra, docs, growth | Create these Jira components to classify work.
Custom Field | Recommended Fields | Product Area, Customer Impact, Severity, Environment, Source, Release Target, Docs Required, Compliance Impact, On-chain Impact, AI Involvement | These fields make Jira useful as a business operating system.
Rule | Master Rule | Nothing important lives only in chat | Every feature, bug, incident, change, and release should enter Jira.
Rule | Definition of Done | Code + validation + docs + release/change linkage + monitoring follow-up if needed | Do not close work before the business context is complete.
Google | Workspace Role | Docs for narrative context, Sheets for dashboards, Calendar/Meet for cadence | Google supports Jira; it should not replace Jira.
Progress | Solana Phase Two | In Progress | Governance-aware proposal_pending wallet state implemented; Squads rollout prep is the next active step.

## Epics
Initiative | Epic Summary | Goal | Priority | Components | Labels | Source Plan
Solana Testnet Enablement | Harden Solana Execution Path | Make live testnet whitelist sync safe with startup guards, readiness checks, logging, and rollback discipline. | Highest | solana, api-gateway, security | initiative:solana-testnet, area:solana | docs/plans/SOLANA_TESTNET_ENABLEMENT_PLAN.md
Solana Testnet Enablement | Deploy and Verify Wallet Whitelist on Testnet | Fund the signer, deploy the wallet whitelist program, capture the real testnet program ID, and verify explorer visibility. | Highest | solana, infra | initiative:solana-testnet, area:solana | docs/plans/SOLANA_TESTNET_ENABLEMENT_PLAN.md
Solana Testnet Enablement | Configure Testnet Runtime and Canary | Set Railway env, inject signer secrets, run the first wallet canary, and prove rollback back to preview mode. | Highest | solana, infra, api-gateway | initiative:solana-testnet, area:solana, env:testnet | docs/plans/SOLANA_TESTNET_ENABLEMENT_PLAN.md
Solana Testnet Enablement | Evaluate Solana Phase Two | Decide whether to add Squads multisig, improved wallet pending states, and optional KYC on-chain sync after the first canary. | Medium | solana, governance, kyc | initiative:solana-testnet, area:solana | docs/plans/SOLANA_TESTNET_ENABLEMENT_PLAN.md
AI Advisory Layer | Choose AI Provider and Governance Model | Decide the provider, hosting posture, residency, retention, and compliance constraints for AI in TreasuryOS. | High | ai, security | initiative:ai-advisory, area:ai | docs/plans/AI_ADVISORY_LAYER_IMPLEMENTATION_PLAN.md
AI Advisory Layer | Design AI Storage, Redaction, and Auditability | Define and harden advisory schemas, redaction rules, and auditable storage; operator feedback capture remains a follow-up. | High | ai, security, audit | initiative:ai-advisory, area:ai | docs/plans/AI_ADVISORY_LAYER_IMPLEMENTATION_PLAN.md
AI Advisory Layer | Build AI Module Foundation | Add the API gateway AI module, provider abstraction, feature flags, typed outputs, and no-signer boundaries for the first advisory slice. | High | ai, api-gateway | initiative:ai-advisory, area:ai | docs/plans/AI_ADVISORY_LAYER_IMPLEMENTATION_PLAN.md
AI Advisory Layer | Ship Read-only AI Advisories | Ship transaction-case advisories first and expand to additional read-only AI surfaces only after the first slice is stable. | Medium | ai, transaction-cases, reports, audit | initiative:ai-advisory, area:ai | docs/plans/AI_ADVISORY_LAYER_IMPLEMENTATION_PLAN.md
Product Operations | Establish Jira Operating Backbone | Create the Jira structure, fields, boards, and workflow rules that make TreasuryOS manageable as a real business product. | Highest | docs, infra | initiative:ops, area:ops | session plan
Product Operations | Build Google Product Ops Hub | Create Drive folders, Docs templates, Sheets dashboards, and meeting-note assets that support Jira. | High | docs, growth | initiative:ops, area:ops | session plan
Product Operations | Release, Bug, and Incident Discipline | Operationalize release tracking, bug triage, incident handling, and postmortem routines. | High | docs, security, infra | initiative:ops, area:ops | session plan
Product Operations | Executive Reporting and Portfolio Review | Create dashboards and recurring reviews for product status, bug trends, release readiness, and strategic risk. | Medium | docs, growth, infra | initiative:ops, area:ops | session plan
Growth & Customer Experience | Customer Feedback and Conversion Ops | Capture customer requests, conversion learnings, and landing/demo improvements in the same product operating model. | Medium | growth, landing-page, docs | initiative:growth, area:growth | NEXT_ACTIONS.md
Platform Reliability | Reliability and Hardening Backlog | Track protocol audit, infra provisioning, and unresolved operational warnings as structured product work. | High | infra, security, api-gateway | initiative:platform-ops, area:infra | NEXT_ACTIONS.md

## Active Tickets
Initiative | Epic | Issue Type | Summary | Priority | Board Status | Components | Labels | Environment | Source | Source Todo ID | Depends On | Description | Acceptance Criteria
Product Operations | Establish Jira Operating Backbone | Task | Establish Jira project structure | Highest | Ready | docs, infra | initiative:ops, area:ops | n/a | founder | plan-jira-product-ops |  | Create the company-managed Jira project, issue types, components, custom fields, and boards that TreasuryOS will use as the operational source of truth. | Jira project exists; components created; fields created; main board and saved filters exist.
Product Operations | Establish Jira Operating Backbone | Task | Define Jira workflows and standards | High | Backlog | docs, infra | initiative:ops, area:ops | n/a | founder | define-jira-workflows-and-standards | Establish Jira project structure | Define feature, bug, incident, change, and release workflows plus the minimum required fields and definitions of ready and done. | Workflows documented; required fields defined; definition of done agreed.
Product Operations | Establish Jira Operating Backbone | Task | Map current plans into Jira portfolio | High | Backlog | docs, infra | initiative:ops, area:ops | n/a | founder | map-current-plans-into-jira-portfolio | Establish Jira project structure; Define Jira workflows and standards | Convert the existing Solana, AI, platform, and growth plans into Jira initiatives or epics with linked stories, tasks, bugs, and release work. | All current plans exist in Jira as structured portfolio items with owners and priorities.
Product Operations | Build Google Product Ops Hub | Task | Create Google product ops hub | High | Backlog | docs, growth | initiative:ops, area:ops | n/a | founder | create-google-product-ops-hub | Establish Jira project structure | Set up the Google Drive, Docs, Sheets, and meeting template structure that supports Jira with PRDs, release checklists, incident docs, dashboards, and notes. | Drive structure created; templates created; dashboards seeded.
Product Operations | Release, Bug, and Incident Discipline | Task | Establish release, bug, and incident routines | High | Backlog | docs, infra, security | initiative:ops, area:ops | n/a | founder | establish-release-bug-incident-routines | Define Jira workflows and standards; Create Google product ops hub | Operationalize release tracking, bug triage, incident handling, postmortems, and the rule that meaningful changes need linked change or release records. | Routines documented; templates linked; first release/incident examples created.
Product Operations | Executive Reporting and Portfolio Review | Task | Build executive product reporting | Medium | Backlog | docs, growth, infra | initiative:ops, area:ops | n/a | founder | build-executive-product-reporting | Map current plans into Jira portfolio; Create Google product ops hub | Create the reporting layer for product status, release readiness, bug trends, platform risk, and customer-impact visibility using Jira dashboards plus Google Sheets or Docs. | Executive dashboard exists; release, bug, and risk views are visible.
Product Operations | Executive Reporting and Portfolio Review | Task | Run first portfolio operating cycle | Medium | Backlog | docs, growth, infra | initiative:ops, area:ops | n/a | founder | run-first-portfolio-operating-cycle | Map current plans into Jira portfolio; Establish release, bug, and incident routines; Build executive product reporting | Run the first full management cycle using the new Jira and Google model so TreasuryOS work is reviewed as a business portfolio rather than as isolated technical tasks. | One full review cycle completed with next actions, release view, and risks updated.
Solana Testnet Enablement | Harden Solana Execution Path | Task | Harden Solana sync guards | Highest | Ready for Release | solana, api-gateway, security | initiative:solana-testnet, area:solana, env:testnet | testnet-canary | docs/reports/SOLANA_TESTNET_RUNTIME_SETUP_REPORT.md | harden-solana-sync-guards |  | Add startup and readiness protections so the API refuses live Solana sync when testnet RPC, signer material, or wallet whitelist program configuration is missing or invalid. | API fails fast on bad live-sync config; readiness path verifies RPC, signer, and program existence.
Solana Testnet Enablement | Deploy and Verify Wallet Whitelist on Testnet | Task | Deploy wallet whitelist program to testnet | Highest | Released | solana, infra | initiative:solana-testnet, area:solana, env:testnet | testnet-canary | docs/reports/SOLANA_TESTNET_DEPLOYMENT_WORKLOG.md | deploy-wallet-whitelist-testnet |  | Deploy the wallet whitelist program to Solana testnet, verify the final program ID, and record the authority and signer details needed by the API. | Program deployed; final program ID recorded; explorer and CLI verification complete.
Solana Testnet Enablement | Configure Testnet Runtime and Canary | Change | Configure testnet signer env | Highest | Released | solana, infra, api-gateway | initiative:solana-testnet, area:solana, env:testnet | testnet-canary | docs/reports/SOLANA_TESTNET_RUNTIME_SETUP_REPORT.md | configure-testnet-signer-env | Deploy wallet whitelist program to testnet | Update Railway API variables for SOLANA_RPC_URL, SOLANA_NETWORK, PROGRAM_ID_WALLET_WHITELIST, SOLANA_SIGNING_MODE, AUTHORITY_KEYPAIR_JSON, and keep SOLANA_SYNC_ENABLED=false until validation is complete. | Railway env updated, signer loads correctly, readiness is green, and the testnet runtime supports the completed canary path.
Solana Testnet Enablement | Configure Testnet Runtime and Canary | Change | Run testnet wallet canary | Highest | Released | solana, api-gateway | initiative:solana-testnet, area:solana, env:testnet | testnet-canary | docs/reports/SOLANA_TESTNET_DEPLOYMENT_WORKLOG.md | run-testnet-wallet-canary | Harden Solana sync guards; Deploy wallet whitelist program to testnet; Configure testnet signer env | Approve a controlled wallet through the API or dashboard with SOLANA_SYNC_ENABLED=true and verify chainSyncStatus, stored signature, explorer visibility, and rollback. | Real testnet signature stored, whitelist entry verified, and the canary result documented.
Solana Testnet Enablement | Evaluate Solana Phase Two | Spike | Evaluate Solana phase two | Medium | In Progress | solana, governance, kyc | initiative:solana-testnet, area:solana | testnet | docs/reports/PHASE_TWO_GOVERNANCE_PENDING_STATUS_REPORT.md | evaluate-solana-phase-two | Run testnet wallet canary | After the successful direct-signer canary, harden governance-aware wallet states, prepare the Squads testnet rollout, and decide whether to expand into broader on-chain compliance sync. | Governance-aware pending-state behavior is implemented and the next rollout steps are documented.
AI Advisory Layer | Choose AI Provider and Governance Model | Spike | Choose AI provider model | High | Ready | ai, security | initiative:ai-advisory, area:ai | ai-phase-1 | founder | choose-ai-provider-model |  | Decide whether TreasuryOS should use an external managed model, a self-hosted model, or defer the provider choice until after the first advisory prototype, including residency and retention constraints. | Provider/hosting decision recorded with compliance and retention notes.
AI Advisory Layer | Design AI Storage, Redaction, and Auditability | Task | Harden AI storage and redaction foundation | High | In Progress | ai, audit, security | initiative:ai-advisory, area:ai | ai-phase-1 | docs/reports/AI_ADVISORY_FOUNDATION_REPORT.md | harden-ai-storage-redaction-foundation | Choose AI provider model | Implement the first advisory schema, redaction profile, persistent ai_advisories storage, and auditability model for transaction-case summaries while leaving operator feedback capture as a later increment. | The first advisory slice persists safely with a redaction profile and audit trail, and the remaining feedback work is explicit.
AI Advisory Layer | Build AI Module Foundation | Task | Implement AI module foundation | High | Released | ai, api-gateway | initiative:ai-advisory, area:ai | ai-phase-1 | docs/reports/AI_ADVISORY_FOUNDATION_REPORT.md | implement-ai-module-foundation | Design AI storage and redaction | Add the API gateway AI module, deterministic provider abstraction, feature flags, typed advisory outputs, and strict no-authority boundaries for approvals or Solana signing. | The AI module ships behind flags with typed outputs, a transaction-case advisory endpoint, and no signer or approval authority.
AI Advisory Layer | Ship Read-only AI Advisories | Story | Ship transaction-case AI advisories | Medium | Released | ai, transaction-cases, dashboard, audit | initiative:ai-advisory, area:ai | ai-phase-1 | docs/reports/AI_ADVISORY_FOUNDATION_REPORT.md | ship-transaction-case-ai-advisories | Implement AI module foundation | Deliver the first low-risk AI feature through the API and dashboard: transaction-case summaries, recommendations, risk factors, and operator checklists without coupling AI to approval or chain execution paths. | Operators can view the AI advisory card on transaction-case detail pages, the feature is flag-gated, and no approval path depends on AI.
Platform Reliability | Reliability and Hardening Backlog | Task | Audit Railway API warnings | Medium | Blocked | infra, api-gateway | initiative:platform-ops, area:infra | beta-hardening | monitoring | audit-railway-api-warnings |  | Inspect the Railway API service warnings, determine risk for beta launch, document findings, and recommend or apply the safest next actions. | Warning source understood; risk classified; remediation or documented waiver agreed.
Solana Testnet Enablement | Evaluate Solana Phase Two | Task | Implement governance-aware wallet states | High | In Progress | solana, governance, api-gateway, dashboard | initiative:solana-testnet, area:solana, phase:two | testnet | docs/reports/PHASE_TWO_GOVERNANCE_PENDING_STATUS_REPORT.md | phase-two-wallet-statuses | Run testnet wallet canary | Add proposal-pending wallet semantics across shared types, API approval flow, transaction screening, audit events, and dashboard wallet views so Squads proposals no longer look fully approved. | Squads proposal approvals land in proposal_pending, operator messaging is clear, and downstream screening remains blocked until execution.
Solana Testnet Enablement | Evaluate Solana Phase Two | Task | Prepare Squads testnet rollout | High | Ready | solana, governance, infra | initiative:solana-testnet, area:solana, blocked:external-values | testnet | docs/reports/PHASE_TWO_GOVERNANCE_PENDING_STATUS_REPORT.md | phase-two-governance-prep | Implement governance-aware wallet states | Document the remaining external setup for testnet Squads rollout: create the multisig, confirm signer set and threshold, inject env values, and run the first governed wallet execution. | Multisig details, runtime inputs, and the governed execution checklist are ready for the next rollout step.

## Jira Import
Import Pass | Issue Type | Summary | Epic Name | Epic Link / Parent Epic | Priority | Board Status | Components | Labels | Environment | Source | Description | Acceptance Criteria
1 | Epic | Harden Solana Execution Path | Harden Solana Execution Path |  | Highest | Ready for Release | solana, api-gateway, security | initiative:solana-testnet, area:solana | testnet | docs/reports/SOLANA_TESTNET_RUNTIME_SETUP_REPORT.md | Make live testnet whitelist sync safe with startup guards, readiness checks, logging, and rollback discipline. | Startup and readiness protections exist for live Solana sync.
1 | Epic | Deploy and Verify Wallet Whitelist on Testnet | Deploy and Verify Wallet Whitelist on Testnet |  | Highest | Released | solana, infra | initiative:solana-testnet, area:solana | testnet | docs/reports/SOLANA_TESTNET_DEPLOYMENT_WORKLOG.md | Fund the signer, deploy the wallet whitelist program, capture the real testnet program ID, and verify explorer visibility. | Program deployed and verified on testnet.
1 | Epic | Configure Testnet Runtime and Canary | Configure Testnet Runtime and Canary |  | Highest | Released | solana, infra, api-gateway | initiative:solana-testnet, area:solana | testnet | docs/reports/SOLANA_TESTNET_RUNTIME_SETUP_REPORT.md | Set Railway env, inject signer secrets, run the first wallet canary, and prove rollback. | Canary succeeds and rollback back to preview mode is proven.
1 | Epic | Evaluate Solana Phase Two | Evaluate Solana Phase Two |  | Medium | In Progress | solana, governance, kyc | initiative:solana-testnet, area:solana | testnet | docs/reports/PHASE_TWO_GOVERNANCE_PENDING_STATUS_REPORT.md | After the successful direct-signer canary, harden governance-aware wallet states, prepare the Squads testnet rollout, and decide whether to expand into broader on-chain compliance sync. | Governance-aware pending-state behavior is implemented and the next rollout steps are documented.
1 | Epic | Choose AI Provider and Governance Model | Choose AI Provider and Governance Model |  | High | Ready | ai, security | initiative:ai-advisory, area:ai | n/a | docs/plans/AI_ADVISORY_LAYER_IMPLEMENTATION_PLAN.md | Decide provider, hosting posture, residency, retention, and compliance constraints for AI. | Provider and governance posture agreed.
1 | Epic | Design AI Storage, Redaction, and Auditability | Design AI Storage, Redaction, and Auditability |  | High | In Progress | ai, audit, security | initiative:ai-advisory, area:ai | n/a | docs/reports/AI_ADVISORY_FOUNDATION_REPORT.md | Define and harden advisory schemas, redaction rules, and auditable storage; operator feedback capture remains a follow-up. | First advisory storage and redaction ship with auditability, and the remaining feedback layer is clearly queued.
1 | Epic | Build AI Module Foundation | Build AI Module Foundation |  | High | Released | ai, api-gateway | initiative:ai-advisory, area:ai | n/a | docs/reports/AI_ADVISORY_FOUNDATION_REPORT.md | Add the API gateway AI module, provider abstraction, feature flags, typed outputs, and no-signer boundaries for the first advisory slice. | AI module foundation is shipped behind flags and remains outside approval and signing paths.
1 | Epic | Ship Read-only AI Advisories | Ship Read-only AI Advisories |  | Medium | In Progress | ai, transaction-cases, reports, audit | initiative:ai-advisory, area:ai | n/a | docs/reports/AI_ADVISORY_FOUNDATION_REPORT.md | Ship transaction-case advisories first and expand to additional read-only AI surfaces only after the first slice is stable. | Operators can already view transaction-case advisories and the next read-only surfaces are queued deliberately.
1 | Epic | Establish Jira Operating Backbone | Establish Jira Operating Backbone |  | Highest | Ready | docs, infra | initiative:ops, area:ops | n/a | session plan | Create the Jira structure, fields, boards, and workflow rules for TreasuryOS. | Jira operating backbone exists.
1 | Epic | Build Google Product Ops Hub | Build Google Product Ops Hub |  | High | Backlog | docs, growth | initiative:ops, area:ops | n/a | session plan | Create Drive folders, Docs templates, Sheets dashboards, and meeting assets. | Google ops hub exists.
1 | Epic | Release, Bug, and Incident Discipline | Release, Bug, and Incident Discipline |  | High | Backlog | docs, infra, security | initiative:ops, area:ops | n/a | session plan | Operationalize release tracking, bug triage, incident handling, and postmortems. | Operational routines are in place.
1 | Epic | Executive Reporting and Portfolio Review | Executive Reporting and Portfolio Review |  | Medium | Backlog | docs, growth, infra | initiative:ops, area:ops | n/a | session plan | Create dashboards and recurring portfolio reviews for status, bugs, releases, and risk. | Executive reporting works from Jira and Google.
2 | Task | Establish Jira project structure |  | Establish Jira Operating Backbone | Highest | Ready | docs, infra | initiative:ops, area:ops | n/a | founder | Create the company-managed Jira project, issue types, components, custom fields, and boards. | Project, fields, and main boards exist.
2 | Task | Define Jira workflows and standards |  | Establish Jira Operating Backbone | High | Backlog | docs, infra | initiative:ops, area:ops | n/a | founder | Define feature, bug, incident, change, and release workflows plus definitions of ready and done. | Workflow standards documented and agreed.
2 | Task | Map current plans into Jira portfolio |  | Establish Jira Operating Backbone | High | Backlog | docs, infra | initiative:ops, area:ops | n/a | founder | Convert the existing Solana, AI, platform, and growth plans into Jira epics and linked issues. | Current plans exist in Jira with owners and priorities.
2 | Task | Create Google product ops hub |  | Build Google Product Ops Hub | High | Backlog | docs, growth | initiative:ops, area:ops | n/a | founder | Set up the Google Drive, Docs, Sheets, and meeting template structure that supports Jira. | Drive structure and templates are created.
2 | Task | Establish release, bug, and incident routines |  | Release, Bug, and Incident Discipline | High | Backlog | docs, infra, security | initiative:ops, area:ops | n/a | founder | Operationalize release tracking, bug triage, incident handling, postmortems, and linked change records. | Release and incident routines are adopted.
2 | Task | Build executive product reporting |  | Executive Reporting and Portfolio Review | Medium | Backlog | docs, growth, infra | initiative:ops, area:ops | n/a | founder | Create dashboards for product status, bug trends, release readiness, and platform risk. | Executive dashboard and reporting cadence exist.
2 | Task | Run first portfolio operating cycle |  | Executive Reporting and Portfolio Review | Medium | Backlog | docs, growth, infra | initiative:ops, area:ops | n/a | founder | Run the first full management cycle using the new Jira and Google model. | One full portfolio review cycle is completed.
2 | Task | Harden Solana sync guards |  | Harden Solana Execution Path | Highest | Ready for Release | solana, api-gateway, security | initiative:solana-testnet, area:solana | testnet | docs/reports/SOLANA_TESTNET_RUNTIME_SETUP_REPORT.md | Add startup and readiness protections so the API refuses bad live Solana sync configuration. | Bad live-sync config is rejected; readiness verifies RPC, signer, and program.
2 | Task | Deploy wallet whitelist program to testnet |  | Deploy and Verify Wallet Whitelist on Testnet | Highest | Released | solana, infra | initiative:solana-testnet, area:solana | testnet | docs/reports/SOLANA_TESTNET_DEPLOYMENT_WORKLOG.md | Deploy the wallet whitelist program to Solana testnet, verify the final program ID 3ZaNXXp99xnWYYcaCJMJWnBfMxj2K4QpHkADV8D7321c, and capture explorer verification plus authority details. | Program deployed and verified on testnet with explorer proof and authority details recorded.
2 | Change | Configure testnet signer env |  | Configure Testnet Runtime and Canary | Highest | Released | solana, infra, api-gateway | initiative:solana-testnet, area:solana, blocked:external-values | testnet | docs/reports/SOLANA_TESTNET_RUNTIME_SETUP_REPORT.md | Apply the deployed testnet program ID, dedicated signer secret, and preview-safe settings to the Railway API service, then verify /api/health/ready before the first canary. | Railway env updated, signer loads correctly, readiness is green, and the runtime supports the completed canary path.
2 | Change | Run testnet wallet canary |  | Configure Testnet Runtime and Canary | Highest | Released | solana, api-gateway | initiative:solana-testnet, area:solana | testnet | docs/reports/SOLANA_TESTNET_DEPLOYMENT_WORKLOG.md | Approve a controlled wallet through the API or dashboard with live sync enabled and verify the signature plus rollback. | Real testnet signature stored, whitelist entry verified, and the canary result documented.
2 | Spike | Evaluate Solana phase two |  | Evaluate Solana Phase Two | Medium | In Progress | solana, governance, kyc | initiative:solana-testnet, area:solana | testnet | docs/reports/PHASE_TWO_GOVERNANCE_PENDING_STATUS_REPORT.md | After the successful direct-signer canary, harden governance-aware wallet states, prepare the Squads testnet rollout, and decide whether to expand into broader on-chain compliance sync. | Governance-aware pending-state behavior is implemented and the next rollout steps are documented.
2 | Spike | Choose AI provider model |  | Choose AI Provider and Governance Model | High | Ready | ai, security | initiative:ai-advisory, area:ai | n/a | founder | Decide whether TreasuryOS should use an external managed model, a self-hosted model, or defer the provider choice. | Provider choice documented with compliance constraints.
2 | Task | Harden AI storage and redaction foundation |  | Design AI Storage, Redaction, and Auditability | High | In Progress | ai, audit, security | initiative:ai-advisory, area:ai | n/a | docs/reports/AI_ADVISORY_FOUNDATION_REPORT.md | Implement the first advisory schema, redaction profile, persistent ai_advisories storage, and auditability model for transaction-case summaries while leaving operator feedback capture as a later increment. | The first advisory slice persists safely with a redaction profile and audit trail, and the remaining feedback work is explicit.
2 | Task | Implement AI module foundation |  | Build AI Module Foundation | High | Released | ai, api-gateway | initiative:ai-advisory, area:ai | n/a | docs/reports/AI_ADVISORY_FOUNDATION_REPORT.md | Add the API gateway AI module, deterministic provider abstraction, feature flags, typed advisory outputs, and strict no-authority boundaries for approvals or Solana signing. | The AI module ships behind flags with typed outputs, a transaction-case advisory endpoint, and no signer or approval authority.
2 | Story | Ship transaction-case AI advisories |  | Ship Read-only AI Advisories | Medium | Released | ai, transaction-cases, dashboard, audit | initiative:ai-advisory, area:ai | n/a | docs/reports/AI_ADVISORY_FOUNDATION_REPORT.md | Deliver the first low-risk AI feature through the API and dashboard: transaction-case summaries, recommendations, risk factors, and operator checklists without coupling AI to approval or chain execution paths. | Operators can view the AI advisory card on transaction-case detail pages, the feature is flag-gated, and no approval path depends on AI.
2 | Task | Audit Railway API warnings |  | Reliability and Hardening Backlog | Medium | Blocked | infra, api-gateway | initiative:platform-ops, area:infra | production | monitoring | Inspect the Railway API service warnings, determine risk, document findings, and recommend or apply the safest next actions. | Warning source understood and risk classified.
2 | Task | Implement governance-aware wallet states |  | Evaluate Solana Phase Two | High | In Progress | solana, governance, api-gateway, dashboard | initiative:solana-testnet, area:solana, phase:two | testnet | docs/reports/PHASE_TWO_GOVERNANCE_PENDING_STATUS_REPORT.md | Add proposal-pending wallet semantics across shared types, API approval flow, transaction screening, audit events, and dashboard wallet views so Squads proposals no longer look fully approved. | Squads proposal approvals land in proposal_pending, operator messaging is clear, and downstream screening remains blocked until execution.
2 | Task | Prepare Squads testnet rollout |  | Evaluate Solana Phase Two | High | Ready | solana, governance, infra | initiative:solana-testnet, area:solana, blocked:external-values | testnet | docs/reports/PHASE_TWO_GOVERNANCE_PENDING_STATUS_REPORT.md | Document the remaining external setup for testnet Squads rollout: create the multisig, confirm signer set and threshold, inject env values, and run the first governed wallet execution. | Multisig details, runtime inputs, and the governed execution checklist are ready for the next rollout step.

## Roadmap Backlog
Track | Issue Type | Summary | Priority | Components | Release Target | Source | Notes
Platform Reliability | Task | Protocol audit for Anchor programs | High | security, solana | post-beta | NEXT_ACTIONS.md | Hire a third-party security firm to audit the Anchor programs and Rust permissioning logic.
Platform Reliability | Task | Infrastructure provisioning hardening | High | infra, security | post-beta | NEXT_ACTIONS.md | Harden the managed Railway, Vercel, and Cloudflare stack for production traffic.
Real-World Connectivity | Epic | Banking integration | High | infra, api-gateway | future | NEXT_ACTIONS.md | Secure production mTLS certificates for Amina and SWIFT and implement the live ISO20022 relay.
Real-World Connectivity | Epic | Sumsub webhooks | High | kyc, api-gateway | future | NEXT_ACTIONS.md | Connect the KYC service to live Sumsub webhooks for automated entity status transitions.
Real-World Connectivity | Epic | Solana mainnet and fee management | High | solana, infra | future | NEXT_ACTIONS.md | Set up dedicated RPC and fee-management posture for a later mainnet path.
AI Advisory Layer | Epic | AI-assisted screening evolution | Medium | ai, transaction-cases | future | NEXT_ACTIONS.md | Expand advisory AI toward richer screening assistance only after read-only and decision-support phases are proven.
Growth & Customer Experience | Epic | Customer feedback and conversion ops | Medium | growth, landing-page, docs | always-on | session plan | Capture customer requests, landing conversion learnings, and demo journey issues inside the same product operating model.

## Workflows
Workflow Family | Step Order | Status | Usage Notes
Feature | 1 | Backlog | Idea captured, not yet prioritized.
Feature | 2 | Ready | Clear scope, owner, acceptance criteria, and links.
Feature | 3 | In Progress | Actively being implemented.
Feature | 4 | In Review | Code, design, or stakeholder review in progress.
Feature | 5 | Ready for Release | Validation and docs complete; waiting to ship.
Feature | 6 | Released | Live and communicated.
Feature | 7 | Blocked | Cannot proceed because of dependency or decision gap.
Bug | 1 | New | Reported but not yet confirmed.
Bug | 2 | Confirmed | Reproduced and scoped.
Bug | 3 | Ready | Planned with owner and severity.
Bug | 4 | In Progress | Fix underway.
Bug | 5 | In Validation | Fix deployed or under test.
Bug | 6 | Ready for Release | Verified and queued for ship.
Bug | 7 | Released | Fix is live.
Bug | 8 | Won't Fix / Deferred | Intentionally not shipping now; reason documented.
Incident | 1 | New | Production issue created.
Incident | 2 | Investigating | Actively diagnosing.
Incident | 3 | Mitigated | Immediate harm reduced.
Incident | 4 | Monitoring | Watching system after mitigation.
Incident | 5 | Resolved | Impact ended.
Incident | 6 | Postmortem Required | Recovery complete but learning work still open.
Incident | 7 | Closed | Postmortem linked and follow-up tracked.
Change / Release | 1 | Planned | Scope and validation path drafted.
Change / Release | 2 | Approved | Ready to execute.
Change / Release | 3 | In Execution | Deployment or config change underway.
Change / Release | 4 | Monitoring | Watching after execution.
Change / Release | 5 | Completed | Change landed successfully.
Change / Release | 6 | Rolled Back | Change reversed; follow-up issue required.

## Google Ops
Type | Name | Purpose | Frequency / Trigger | Owner
Folder | 01 Strategy and Roadmap | Product strategy, initiative docs, roadmap snapshots, and decision logs. | Always on | Product owner / founder
Folder | 02 Product Specs | PRDs, feature specs, and customer-flow docs. | Always on | Product owner
Folder | 03 Releases and Change Logs | Release checklists, release notes, change records, and rollback docs. | Per release | Engineering lead / founder
Folder | 04 Bugs and Incidents | Bug evidence, incident reports, and postmortems. | As needed | Engineering / ops
Folder | 05 Customer and Market Feedback | Customer requests, sales notes, demo feedback, and market learnings. | Always on | Founder / growth
Folder | 06 Executive Dashboards | Leadership views, KPI snapshots, and risk reporting. | Weekly / monthly | Founder
Folder | 07 Compliance and Audit Notes | Compliance decisions, audit notes, and policy references. | As needed | Compliance owner
Folder | 08 Meeting Notes | Recurring ceremony notes and action logs. | Recurring | Meeting owner
Doc Template | PRD Template | Feature problem, users, acceptance criteria, risks, rollout, and metrics. | Per feature | Product owner
Doc Template | Bug Report Template | Environment, repro steps, expected vs actual, severity, evidence. | Per bug | Reporter / owner
Doc Template | Incident Report Template | Symptoms, impact, timeline, mitigation, owner, current status. | Per incident | Incident commander
Doc Template | Postmortem Template | Root cause, lessons, action items, linked Jira issues. | After incident | Incident owner
Doc Template | Release Checklist Template | Scope, validation, rollback, docs, communications, monitoring. | Per release | Release owner
Doc Template | Customer Feedback Note | Problem, request, source account, urgency, follow-up. | Per insight | Founder / CS
Doc Template | Decision Log | Context, options, decision, owner, consequences. | Per major decision | Decision maker
Sheet | Feature Status Dashboard | Live status by epic, owner, and release target. | Weekly refresh | Product owner
Sheet | Bug Heatmap | Counts by severity, component, and environment. | Weekly refresh | Engineering lead
Sheet | Release Log | Release dates, scope, status, and follow-ups. | Per release | Release owner
Sheet | Customer Request Tracker | Track market/customer pull and priorities. | Weekly refresh | Founder / growth
Sheet | KPI Dashboard | Product, delivery, and reliability KPIs for leadership. | Monthly refresh | Founder

## Cadence
Cadence | Meeting | Owner | Inputs | Outputs | Tools
Daily | Delivery check-in | Founder / active owners | Ready and in-progress Jira tickets, blockers | Updated board, owner follow-ups, escalations | Jira + Meet
Twice weekly | Bug triage | Engineering / founder | New and confirmed bugs, severity, environments | Prioritized fixes and release targets | Jira + Bug dashboard
Weekly | Portfolio and release review | Founder / product owner | Epics, release issues, blockers, risks | What ships next, what slips, what needs decision | Jira board + Google release sheet
Weekly | Customer and growth review | Founder / growth | Customer feedback tracker, landing metrics, demo feedback | New backlog candidates and priority changes | Google Sheet + Jira
Monthly | Executive KPI and risk review | Founder / leadership | KPI dashboard, release history, top bugs, strategic risks | Leadership decisions, budget/priorities, risk actions | Google KPI sheet + Jira dashboard
As needed | Incident review | Incident commander | Live incident issue and evidence | Mitigation plan and postmortem owner | Jira incident + Meet

## Templates
Issue Type | Summary Template | Required Fields | Done When
Epic | [Area] Outcome to achieve | Problem, goal, success metric, owner, target horizon, linked plan | The epic contains linked work and success is measurable.
Story | [User/Team] Can do X | Problem, user value, acceptance criteria, owner, release target | Validated, documented if needed, and linked to release.
Task | [System/Team] Implement or set up X | Scope, owner, dependencies, validation steps, docs impact | Completed with validation and linked docs/change if needed.
Spike | [Research] Decide X | Question, options, owner, deadline, output expected | Decision or recommendation documented and linked.
Bug | [Component] Short problem summary | Severity, environment, repro steps, expected vs actual, evidence | Fix validated or explicit defer/wont-fix reason recorded.
Incident | [Prod] Service degradation summary | Impact, timeline, owner, mitigation, customer effect, follow-up links | Resolved, monitored, and postmortem linked before closure.
Change | [Env/Service] Controlled change summary | Planned change, approvals, rollback, validation, monitoring | Executed or rolled back with evidence and follow-ups.
Release | TreasuryOS Release YYYY-MM-DD | Included items, rollout steps, rollback path, comms, monitoring | Release shipped with verification and linked scope.